## Project Flow
|  |  | Test Script Registration Flow | [5 empty] | Test script uses FVT Wacthdog Flow
Web page
Test script name
Test script Rev
Station
Assembly Number
Assembly Rev
[6 empty] | TE Lead | TE Lead
|  |  |  | TE lead |  | SME Lead | SME Lead
| Input to script comand: | Test script ID
Current test script File's Hash String
| Output: | test script ID
Reference File's Hash String
|  |  | FVT Wacthdog test script file's Hash verification Flow in TE WS |  |  |  |  | FVT Wacthdog SP re-active the previous test script after expiring for Deviation |  | FVT Wacthdog monitor if there is unregisterred test script is using in production Flow
Start
Test Engineer submits the encrypted test script information to request a test script ID.
New test script?
Approve?
System release a test script ID
Test Engineer finalize the test script to apply FVT watch dog with the released test script ID
Test Engineer attach the final test script and ecrypted test script.
End
PCN/ECN/ECO?
Deviation?
Approve?
System release a new test script ID and deavtive the old test script ID
Approve?
System release a new test script ID and temporarily deavtive the old test script ID(active the expiration of the new test scrip ID in 60 days)
Start
Check UUT's SN OkToTest with Test script file's Hash check. and record a log in system's DB
Ok?
Perform normal Test process
End
Start
Get test script ID and used test script file's Hash from the test script.
The file's Hash is matching?
Check UUT's process OkToTest using MES-TIS CheckOkToTest
Return "Pass"
End
Verify the actual file's Hash vs registerred file's Hash using active test script ID in DB
Is UUT OkToTest?
Send Triggerring e-mail to the team
Return "Fail"
Start
Get test script ID epirationt time in DB.
Expiration time<=0?
Active the previous test scrtip ID.
End
Record the request information in a DB
Record the request information in a DB
Start
Get test data per station in MES DB in 30 mins.
Matching?
Record to the App's log
End
Validate the units tested in MES vs request records from the WS.
Send Triggerring e-mail and trigger to the Watchdog client for the hard lock screen.
Record to the App's log
Web System generate an encrypted test script file's Hash (SHA-1) and store in system's DB.
Wrong Test Script file's Hash?
Send trigger e-mail and end the test of this UUT
UUT's SN is wrong process related, end the test of this UUT
Send Triggerring e-mail to the team

## Project Time Line
Project Development Timeline
# | Items | Estimated Needed Time | PIC | WW17 | WW18 | WW19 | WW20 | WW21 | WW22 | WW23
1 | Create a Web Page platform to register test script/test script's change with approval flow, report function(change history, used event log report, test script summary, units tested with non-verified test scripts...)configure for the watchdog application, configure for the user account authentication. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | Vui Le | bar: WW21; WW23
2 | Create a system Data Base to store the test script information and test script used log and support for the web page. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | EdwinM | bar: WW21
3 | Create a centralize storage of test script and backup loaction. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | EdwinM | bar: WW21
4 | Create Store Procedure to trigger and re-activate the test script ID for deviation case after reaching the expriation of deviation. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | EdwinM | bar: WW21
5 | Create a webservice function for test script change verification, record used log in system data base and send trigger e-mail to user groups if there is a test script change. | 1 weeks for development, 1 week for testing. | EdwinM | bar: WW19 to WW20
6 | Create libraries for JEMSTS/JabilTest to use the webservice function for test script change verification. | 1 weeks for development, 1 week for testing. | Huy Nguyen | bar: WW19 to WW20
7 | Create a central watchdog application to monitor the units if these are tested under verified test script, record unit's information, send trigger e-mail and trigger thi client apps to lock screen on the test stations, record apps logs. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | Huy Nguyen | bar: WW21
8 | Create a client watchdog application to stop/lock screen of the tester's PC if there is a unit tested under verified test script. | 2 weeks for develop and 1 week for testing, 1 week for deployment (FOF: Zebra) and validation. | Huy Nguyen | bar: WW21
Note on C10: Nguyen Quochuy: ignore, library will communicate directly to DB.

## Login Page
Log in page using Jabil NTID

## Register Page
Register Page
Items | Remark
Submission Type listbox | new/PCN/Deviation
Test script Name textbox
Test script Rev textbox
Test script description textbox
Customer dropdown list
Station dropdown list
Assembly Number dropown list
Assembly revision dropdown list
Return testscrip ID textbox
Register button
Obsolete/Inactive test script button
Search Test script button
Add configuration file button
Close Deviation button
Extend Deviation button
Download Test script file button

## Watchdog Configuration Page
Watchdog Configuration Page
Items | Remark
Customer dropdown list
Station dropdown list
Tester Name dropdown list
Tester PC Name Textbox
Screen lock trigger check box

## User Role configuration Page
User Role configuration
Items | Remark
Add user feature
Modify user's role and user's information
Remove user.

## Report Page
Report Page
Items | Remark
Summary report for test scripts inventory.
Test script details activities log report.
SN list which used the watchdog system with a time frame.
Active/online test script.